## Team Structure
Team structure
Project Manager	Indira Dossimova
QA Lead	Mika
Automation Engineer	Madina
Product Owner	Elizat Tashpolotova
QA Tester	Zafar Esh
BA	Jenny Salaidinova

## Regression Suite
Regression Test Suite

#	Test Cases	Assigned	Date	Progress	#Test Cases	Pass	Failed
1	Sign Up Testing	Indira		Done	1	1	0
2	Sign In Testing	Madina/Jenny/Elizat		Done	4	4	0
3	Sales Page Testing	Mika/Zafar/Jenny		Done	4	4	0
4	Expenses Page Testing	Indira/Elizat/Mika		Done	4	4	0
5	Reports Page Testing	Zafar/Madina		Done	2	2	0

					15	15	0

## SignUp
Sign Up Test Cases

	TC 1: Sign Up Functionality (Happy Path) - @Indira Dossimova
1	User Navigates to Sign-Up Page (https://cashwise.us/main)
2	User clicks Sign Up Button
3	User Provides email, password and confirms password (all the users information on configuration properties)
4	User clicks Continue Button
5	User provides more personal information and clicks Sign Up button.
6	User validates the header (name of the company).

## SignIn
Sign In Test Cases

	TC 2: Sign In Functionality (Happy Path) - @Madina
1	Given the user is on the "Sign-In" page
2	When the user enters a valid email address "test1234567890@gmail.com"
3	And the user enters a valid password "test1234567890@gmail.com"
4	And the user clicks the "Sign In" button
5	Then the user should be redirected to the "Dashboard" page
6	And the page title should be "Cashwise"
7	And the URL should be "https://cashwise.us/dashboard/infographics”

	TC 2-1: Sign In - Forgot Password Functionality - @Jenny
1	Given User valid email ‘dossimovaib@gmail.com’ and wrong password ‘Indira123’, clicks the login button, gets error message.
2	When User clicks forgot password button, then gets the message ‘Забыли пароль?’ message.
3	Validate the message contains ‘На Ваш Email’ When user sends valid email, clicks the Отправить button, gets the Logotype message Validate the message ‘Ссылка для сброса пароля отправлена’ Validate message contains dossimovaib@gmail.com’, then user didn’t gets the email link, clicks the‘Нажмите сюда’, validate button is clickable.
4	And send the ‘email’ send the отправить button.
5	User doesn’t get the email message.

	TC 2-2: Sign In (Negative Test Cases) - @Elizat
	TC-2.2.1 User provides incorrect email and correct password
1	User navigates to cashwise.us websiteUser clicks SIGN IN button on the main page
2	User provides provides incorrect email (without domain extension )and correct password
3	User clicks the Sign In button
4	User is not able to sign in
5	User validates the message ’Please enter a valid email address
	’Expected: The user shouldn’t be signed in
	A validation message should appear ”Please enter a valid email address”

	TC-2.2.2Sign In with Correct Email and Wrong Password
1	User navigates to cashwise.us website
2	User clicks Sign In button on the main page
3	User provides correct username and wrong password (with 3 characters)
4	User clicks the Sign In button
5	User is not able to Sign In
6	User should validate an error message ’Password must be at least 6 characters
	’Expected : The user should not be signed in. An error message should appear
	Actual: The user is not signed in
	An error message appeared ’Password must be at least 6 characters ’ (edited)

## Sales
Sales Page Test Cases

	TC 3: Sales Button Tabs Check Functionality: @Mika
1	Epic: Sales button functionality
2	User Story: Add a New Client in the Sales Module

	TC 3-1 - Add client button and Adds client Functionality - @Mika
	Then user navigates to the Sales module
	User successfully logs into cashwise.us
	And user views the list of available functionalities And the user selects the “Add Client” functionality
	Then the user fills in all required fields with valid information
	And the user clicks the “Save” button Then the user verifies that the newly added client appears in the client list

	TC 3-2 - Add Products and services functionality - @Zafar
	Given User is on the Dashboard page
	User clicks Sales tab then clicks Add Product and Services link
	User is navigated to Add Product and Services page
	User clicks Add Product and Services button
	User fills out all fields
	Then User validates created Item in the List on a Product and service page

	TC 3-3 - Add Invoice Functionality - @Jenny
	Given user valid email and valid password
	When user clicks the sales button, it gets the ‘clients, product And Service, invoice’ options.
	User clicks invoice button Create invoice and provides information, ‘Indira’ ,
	selects the whom button, ‘03.20.2025’ Payuntil date , and validates company name,Full name clicks Select product service
	chooses Product and Services,user Validates totalSum ‘ ‘, Sumofdiscount ‘,and clicks the save button.

## Expenses
Expenses Page Test Cases

	TC 4-1 - Add Seller - @Indira
1
2
3
4
5
6

	TC-4.2 Add Product and services - @Elizat
1	User provides valid credentials and clicks Sign In button
2	User navigated to the Infographics page and validates the company name
3	User clicks Expenses dropdown and selects Products and services option
4	User navigates to the product page
5	User validates and verifies the title ’Products and services (Expense)’And user clicks ‘add product and services’
6	User provides information: name, price, service type ,category, description, date
7	User chooses remind before and clicks Not repeat box
8	And User clicks Save button
9	And user validates all entered information is correct alt displayed in the Products and services tab
10	User deletes all information and validates the empty list
	Expected Result:
	User successfully navigates through all steps
	The Products and Services (Expense) page displays the correct title
	The newly added Product/Service appears in the tab with all entered details
	User deletes all information and validates the empty list

	TC 4.3 Successfully adding a check: @Mika
1	User successfully logs into cashwise.us
2	When the user navigates to the Expenses module And the user views the list of available functionalities And the user selects the “Check” functionality
3	Then user presses “Add Check” button
4	Then the user fills in all required fields with valid information
5	And the user clicks the “Save” button Then the user verifies that the newly created check appears in the list
6

1
2
3
4
5
6

## Reports
Reports Test Cases

	TC 5-1 - Transactions Add Income - @Zafar

	TC 5-2 - Add expense - @Madina

## Test Metrics
			Test Cases
			#			Tests	Implemented	Automated	Executed	Passed	Failed	Blocked
			1			Sign Up Testing	1	1	1	1	0	0
			2			Sign In Testing	4	4	4	4	0	0
			3			Sales Page Testing	3	3	3	3	0	0
			4			Expenses Page Testing	3	1	3	1	0	0
			5			Reports Page Testing	2	0	2	0	0	0
			6
			7
			8
			9
			10
			11
			12
			13
			14
						Total:	13	9	13	9	0	0

			Test Execution Metrics					%
						Test Case Execution Rate = (Executed Test Cases / Total Test Cases) * 100					100
						Pass Rate = (Passed Test Cases / Executed Test Cases) * 100					69.2307692307692
						Fail Rate = (Failed Test Cases / Executed Test Cases) * 100					0
						Blocked Tests = (Blocked Test Cases / Total Test Cases) * 100					0

			Automation Metrics					%
						Automation Coverage = (Automated Test Cases / Total Test Cases) * 100					69.2307692307692

<class name="com.qa.cashwise.tests.SignUp.SignUpTest"> </class> <class name="com.qa.cashwise.tests.SgnIn.SignInTest"> </class> <class name="com.qa.cashwise.tests.SgnIn.ForgotPasswordLogTest"> </class> <class name="com.qa.cashwise.tests.SgnIn.Negative.SignInTest"> </class> <class name="com.qa.cashwise.tests.SgnIn.Negative.SignInTestData"> </class> <class name="com.qa.cashwise.tests.Sales.InvoiceTest"> </class> <class name="com.qa.cashwise.tests.Sales.ProductAndServicesTest"> </class> <class name="com.qa.cashwise.tests.Sales.ClientsTest"> </class> <class name="com.qa.cashwise.tests.Expenses.ProductAndServicesExpenseTest"> </class>